## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Guests rated the overall tablet experience positively. | 36 of 50 guests (72%) rated the experience 4 or 5 out of 5 (survey Q3). 70% want tablet-only or a mix of tablet and waiter (Q14). Comment: "The tablets were fun!" | Keep the current tablet experience. Use these ratings as the baseline for the full rollout and repeat the survey after launch.
Customers | Went well | Checkout was quick, easy and secure for most guests. | 41 of 50 guests (82%) agreed the checkout was quick, easy and secure (Q10); 66% felt confident or very confident paying on the tablet (Q11). | Add on-screen and waiter guidance for guests who want to pay with cash. Ask Terrific Tablets about phone-based checkout, which one guest asked for.
Customers | Went well | Guests were willing to engage with the tablet's marketing features. | 39 of 50 guests (78%) signed up for the newsletter on the tablet (Q12). | Keep the newsletter sign-up in the tablet flow. Track how many sign-ups turn into repeat visits.
Customers | Needs improvement | Orders were not always prepared correctly. | Only 36 of 50 guests (72%) said their order was correct (Q9), against the 98% target. Examples: wrong entree, missed substitutions, items not left off. | Seydou to check whether a tablet or POS issue is changing order details. Add a modifier and notes review step in the kitchen. Re-measure after fixes.
Customers | Needs improvement | Technical problems with the tablets exceeded the target. | 6 of 50 guests (12%) had technical issues (Q15), against the target of under 5%. Comments: "The screen froze", "It kept freezing but after the waiter did a reboot it was fine". | Ask Terrific Tablets to diagnose the freezing. Keep a log of issues by table. Train waitstaff on a quick reboot and a backup way to order.
Customers | Needs improvement | Guests waited too long for a table. | 27 of 50 guests (54%) waited more than 15 minutes for a table and only 26% waited 10 minutes or less (Q7), against the 10-minute target. | Review host stand and table turn data with the general managers. Test seating flow changes and track lobby wait time every week.
Project team | Went well | Kitchen ticket flow worked well. | Zane: "Tickets came through at a good pace and were easy to keep track of." Larissa: the kitchen has already started updates to operations because of the new ticket flow and is happy with them. | Document the kitchen updates and share them across both locations. Set up the time Peta suggested to review them.
Project team | Went well | Installation worked and technical problems were fixed quickly. | Alex and Gilly: tablets installed and working at both locations. Seydou: POS integration issues were found and fixed quickly. | Update the process manual with each issue and its fix so the solution is easy to find next time.
Project team | Went well | Weekly vendor calls and the survey kept the project on track. | Peta: weekly vendor calls helped the team stay on track and clarify task dependencies. The survey captured meaningful data and most customer satisfaction standards were met. | Recommend keeping weekly vendor calls for the next rollouts. Keep the survey as a standard step.
Project team | Needs improvement | Table turn time did not fall as hoped. | Gilly: "We didn't see as much of a decrease as we wanted." Alex: food came out on time but table turn time stayed about the same. | Help the back of house scale up for higher volume before launch. Review waitstaff training, possibly in two parts that also cover daily service. Track table turn time weekly.
Project team | Needs improvement | Some food orders were still sent back. | Zane: even though ticket flow was smooth, orders still got sent back. Larissa: fewer than before, but still some. Survey: 28% said their order was wrong. | Peta to prioritize analysis. Seydou to check for a technical cause. Run a joint front and back of house session to cut blame and share how each team works.
Project team | Needs improvement | Planning missed availability and location history. | Seydou: implementation took a little longer because vacation time was unaccounted for. Peta: unplanned internal operational issues at each location affected tasks. | Plan around everyone's availability. Review each location's history and operations before planning the next rollout starts.