## Tasks and Timeline
Sauce & Spoon Project Plan
| TASK |  | START DATE | DUE DATE | DURATION | TASK OWNER | STATUS | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | NOTES | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Tablets received
| Generate quotes and review costs |  |  |  | 14 | bar: WEEK 1 F to WEEK 2 T
| Create contracts and statements of work for vendors | Use past contracts for boilerplate |  |  | 5 | bar: WEEK 1 F to WEEK 2 T
| Order tablets | Shipping updated to ~10 days |  |  | 10 | bar: WEEK 2 W
2 | Milestone: Training complete
| Manager training planning |  |  |  | 5 | bar: WEEK 4 M to WEEK 4 R
| Manager training | One day event |  |  | 1 | bar: WEEK 4 M to WEEK 4 R
| GM meeting with staff regarding buy-in | Let Gilly plan this |  |  | 1 | bar: WEEK 4 F to WEEK 5 F
| Waitstaff training planning |  |  |  | 5
| Waitstaff training | One day event |  |  | 1
3 | Milestone: Tablet installation complete
| Book an electrician to install the tablets/wiring | Reference from Deanna |  |  | 8
| Install working tablets in the bar area at the Downtown restaurant locations |  |  |  | 1
| Install working tablets in the bar area at the North restaurant locations |  |  |  | 1
| Sync tablet software with POS | Need to update the POS system |  |  | 7
4 | Milestone: Launch Day complete
| Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 20
| Upload branding to tablets | Connect the marketing team to Terrific Tablets |  |  | 10
| Load menus into the tablets | Waiting on Carter |  |  | 7
| Include messaging about payment security on the tablet | Uploading text |  |  | 1
| Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  |  |  | 14
| Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 13
| Create and implement a post-dining survey to assess customer satisfaction |  |  |  | 3
| Test run planning |  |  |  | 10
| Test run | One day event |  |  | 1
| Launch day | One day event |  |  | 1

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | CONFIDENCE RATING (H/M/L) | KNOWN DATES
Milestone: Tablets received
Generate quotes and review costs |  | 14 | 8 | 14 | 16 | M
Create contracts and statements of work for vendors | Use past contracts for boilerplate | 5 | 3 | 5 | 7 | H
Order and receive tablets | Shipping updated to ~10 days | 10 | 8 | 10 | 12 | M
Milestone: Training complete
Manager training planning |  | 5 | 4 | 5 | 7 | M
Manager training | One day event | 1 | 1 | 1 | 2 | H
GM meeting with staff regarding buy-in | Let Gilly plan this | 1 | 1 | 1 | 2 | H
Waitstaff training planning |  | 5 | 3 | 5 | 8 | M
Waitstaff training | One day event | 1 | 1 | 1 | 2 | H
Milestone: Tablet installation complete
Book an electrician to install the tablets/wiring | Reference from Deanna | 8 | 6 | 8 | 10 | H
Install working tablets in the bar area at the Downtown restaurant locations |  | 1 | 1 | 1 | 2 | H
Install working tablets in the bar area at the North restaurant locations |  | 1 | 1 | 1 | 2 | H
Sync tablet software with POS | Need to update the POS system | 7 | 4 | 7 | 9 | L
Milestone: Launch Day complete
Create a launch day plan: staffing, troubleshooting, etc. |  | 20 | 10 | 20 | 23 | L
Upload branding to tablets | Connect the marketing team to Terrific Tablets | 10 | 6 | 10 | 13 | M
Load menus into the tablets | Waiting on Carter | 7 | 4 | 7 | 9 | L
Include messaging about payment security on the tablet | Uploading text | 1 | 1 | 1 | 3 | H
Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  | 14 | 9 | 14 | 18 | M
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 13 | 7 | 13 | 17 | M
Create and implement a post-dining survey to assess customer satisfaction |  | 3 | 1 | 3 | 5 | H
Test run planning |  | 10 | 7 | 10 | 15 | L
Test run | One day event | 1 | 1 | 1 | 3 | M
Launch day | One day event | 1 | 1 | 1 | 1 | H

## Additional Resouces
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria met?
Customer satisfaction | Average ticket time: apps=8min; entrees=12-15min | How can we improve ticket times? | Ticket times | FALSE
Customer satisfaction | Check-out time: >1min | Are customers satisfied with checkout processes? | Customer satisfication | FALSE
Customer satisfaction | Technical issues: >5% reported | How can we improve customers' ability to use the tablets? | Technical issue reports | FALSE
Customer satisfaction | Order accuracy: 100% | Should we continue using the tablets? | Order accuracy for tablets vs servers | FALSE
Customer satisfaction | Wait time: >10min | How can we improve wait times for customers? | Reported wait times | FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  | Question answer options
Criteria/Description | Survey question | Question type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer satisfaction | During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Customer satisfaction | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
Customer satisfaction | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 - Lacking | 2 | 3 | 4 | 5 - Great
Customer satisfaction | How well did your waiter instruct you how to use the tablet? | Scaled | 1 - Not well | 2 | 3 - Very well
Customer satisfaction | On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 - Difficult | 2 | 3 | 4 | 5 - Easy
Customer satisfaction | On average, how long did you wait for your table? | Scaled | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Customer satisfaction | On average, how long did your dinner take? | Scaled | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min.
Customer satisfaction | Did the kitchen prepare your order correctly? | Yes/No | Yes | No | If no, what went wrong?
Customer satisfaction | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/false | TRUE | FALSE | If you don't agree with the above statement, why?
Customer satisfaction | How confident are you in submitting your payment through a tablet? | Scaled | 1 - Not at all | 2 | 3 | 4 | 5 - Very confident
Customer satisfaction | Did you sign up for the newsletter on the tablet? | Yes/No | Yes | No
Customer satisfaction | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | I liked the tablet experience better, and would like that going forward. | I would like a mix of tablet ordering at the table and waiter interaction. | I disliked the tablets, and would rather have a waiter. | I found both experiences comparable and it doesn't matter either way.
Customer satisfaction | Did you have any technical issues with your tablet? | Open-ended